## Sheet1
Item | Type | Entered | Assigned | Completed | Outcome
How will UI interact with logic | Architecture | 2018-10-05 | Andrew, Conor | 2018-10-08 | Decided on a messaging interface that will allow for complete decoupling
Spinner | Core Feature | 2018-10-05 | Conor | 2018-10-15 | Generates a random number from 1-10
Action Cards | Core Feature | 2018-10-05 | Andrew | 2018-10-06 | Stored in JSON, read in and instances created via a factory.
House Cards | Core Feature | 2018-10-05 | Andrew | 2018-10-06 | Stored in JSON, read in and instances created via a factory.
Career Cards | Core Feature | 2018-10-05 | Andrew | 2018-10-07 | Stored in JSON, read in and instances created via a factory.
College Career Cards | Core Feature | 2018-10-05 | Andrew | 2018-10-07 | Stored in JSON, read in and instances created via a factory.
Board (logic) | Core Feature | 2018-10-05 | Andrew | 2018-10-07 | Implemented using V,E graph to define edges and vertices.
Payday Spaces | Core Feature | 2018-10-05 | Andrew, Conor | 2018-10-18 | Implemented in HandlePlayerMoveState
Action Spaces | Core Feature | 2018-10-05 | Conor | 2018-10-25 | Implemented in HandlePlayerMoveState
Holiday Spaces | Core Feature | 2018-10-05 |  | 2018-10-18 | Implemented in HandlePlayerMoveState
Spin to Win Spaces | Core Feature | 2018-10-05 | Andrew | 2018-10-25 | Implemented as a separate state.
Baby Spaces | Core Feature | 2018-10-05 | Conor | 2018-10-27 | Implemented in HandlePlayerMoveState
House Spaces | Core Feature | 2018-10-05 | Conor | 2018-10-24 | Implemented as a separate state.
Graduation Stop | Core Feature | 2018-10-05 | Andrew | 2018-10-28 | Implemented as a separate state.
Get Married Stop | Core Feature | 2018-10-05 | Andrew | 2018-10-25 | Implemented as a separate state.
Night School Stop | Core Feature | 2018-10-05 | Andrew | 2018-10-25 | Implemented as a separate state.
Family Stop | Core Feature | 2018-10-05 | Andrew | 2018-10-28 | Implemented as a separate state.
Baby Stop | Core Feature | 2018-10-05 | Conor | 2018-10-28 | Implemented as a separate state.
Retirement Stop | Core Feature | 2018-10-05 | Conor | 2018-10-27 | Implemented as a separate state.
Taking out loans | Core Feature | 2018-10-05 | Conor | 2018-10-28 | Forced in all cases apart from house purchase as otherwise it will force bankruptcy
Bank | Core Feature | 2018-10-05 | Andrew | 2018-10-08 | Bank has responsibility for all monetary transactions.
Player Object | Core Feature | 2018-10-05 | Andrew, Conor | 2018-10-07 | Created this object and defined the basic class variables.
Dependants | Core Feature | 2018-10-05 | Andrew | 2018-10-08 | Marital status and dependants implemented.
UI (basic) | Core Feature | 2018-10-05 | Conor | 2018-10-06 | Created a basic UI that will allow us to test the functionality going forward
UI board | Core Feature | 2018-10-05 | Conor | 2018-12-12 | Implemented the board, uses the same configuration file as the VE graph logical board.
UI input | Core Feature | 2018-10-05 | Conor | 2018-10-12 | Button action listeners send messages to the logic and wait for a response.
UI user decision | Core Feature | 2018-10-05 | Andrew, Conor | 2018-10-13 | Binary choice for cards implemented.
UI data display | Core Feature | 2018-10-05 | Conor | 2018-10-08 | Displays the relevant fields stored in the player object to the user
Config imports from json | Core Feature | 2018-10-05 | Andrew | 2018-10-06 | Allows for extensibility.
Maven | Other | 2018-10-06 | Andrew, Conor | 2018-10-06 | n/a
Discuss structure of over-and-back functionality between GamePlayLogic and UI | Architecture | 2018-10-08 | Andrew, Conor | 2018-10-17 | Good progress made on this. We identified the actions that the GUI should handle which were appropriate. Effort was made to reduce any knowledge of underlying implementation of core game logic. Standard message request and responses were laid out. A small subset of all overall messages have been tested, and seem to be an efficient and easily-understood method of transferring required information from the UI to the "backend", and vice-versa.
Config file for resources and "magic" numbers | Core Feature | 2018-10-08 | Conor
For ease of use college and normal careers should inherit a common parent | Architecture | 2018-10-08 | Andrew | 2018-10-12 | Implemented as requested.
JSON parsing utility | Feature Request | 2018-10-08 | Andrew | 2018-10-12 | Implemented as requested.
Implement "ShadowPlayer" as a generic messaging object, rather than impl. Specific player | Feature REquest | 2018-10-11 | Conor | 2018-10-12 | Implemented as requested.
Design interaction of UI with Logic through MessagingInterface object | Architecture | 2018-10-13 | Conor | 2018-10-17 | Interface has been instantiated and basic functionality tested.
Discuss potential architectures for hierarchical state machine | Architecture | 2018-10-17 | Andrew, Conor | 2018-11-01 | Creating state transition diagram for top level & flow for sub levels.
What will initialise the HouseCards, ActionCards, etc. | Architecture | 2018-10-17 | Andrew, Conor | 2018-10-23 | Decided the "bank" would manage this.
Decision messages need a "subject" so that the users knows what they are deciding | Feature Request | 2018-10-23 | Conor | 2018-10-28 | Implemented as requested.
UI needs a better method for displaying choices w/ >2 options | Feature Request | 2018-10-23 | Conor
States should make use of their entry functions | Architecture | 2018-10-24 | Andrew, Conor | 2018-10-27 | Refactored existing code to implement this and used it going forwards where appropriate
How to handle retirement | Architecture | 2018-10-27 | Conor | 2018-10-27 | Retired players to be managed as a separate list, modified how we tracked the current player to fit this method
Make use of exit functions | Architecture | 2018-10-27 | Andrew, Conor | 2018-11-11 | Never had a reason to use this
Merge common state functionality | Coding Style | 2018-10-27 | Andrew, Conor | 2018-11-11 | Refactored existing code to implement this and used it going forwards where appropriate
Write tile (integration) tests | Testing | 2018-10-27 | Andrew, Conor | n/a | Implemented/plan to implent unit tests for all major classes and integration tests for tile interaction sequences.
Get married state loops forever | Bug | 2018-10-27 | Andrew, Conor | 2018-10-30 | Caused by the introduction of retirement, redesigned this state.
Messaging system required to inform user of updates | Feature Request | 2018-10-27 | Conor | 2018-10-29 | String now appears in UI that informs user of happenings in the game
Need to transition to ended state once all players have retired | Missing Feature | 2018-10-27 | Conor | 2018-10-30 | Functionally implemented, untested and ui is v basic for this.
Are retired players immune | Gameplay | 2018-10-27 | Conor | 2018-11-07 | Asked Liliana, the decision is ours. Chose to make them immune.
Potential for "unsupported" methods in GameState interface. | Architecture | 2018-10-27 | Andrew, Conor | 2018-11-11 | Solved in "Merge common state functionality".
Spinner hits someone's bonus | Missing Feature | 2018-10-28 | Andrew | 2018-10-28 | Implemented in HandlePlayerMoveState
HouseChoiceState needs loan handling | Missing Feature | 2018-10-28 | Conor | 2018-10-30 | Implemented as requested.
Reduce the number of methods that take a GameLogic object reference as a parameter | Coding Style | 2018-10-28 | Andrew, Conor | 2018-11-21 | Refactored existing code to implement this and used it going forwards where appropriate
Need to implement fork choices | Missing Feature | 2018-10-28 | Andrew | 2018-11-09 | Implemented as requested.
Spin to win needs an event message in its EndTurnState constructor | Missing Feature | 2018-10-30 | Conor | 2018-10-30 | Implemented as requested.
Error when player 2 retires first | Bug | 2018-10-30 | Conor | 2018-10-30 | Caused by overflow on player index.
ShadowPlayer constructor should not take GameLogic object as parameter | Coding Style | 2018-11-02 | Conor | 2018-11-04 | Replaced with a static method in player.
Remaining Tile Tests | Testing | 2018-11-05 | Andrew, Conor |  | Implemented as requested.
night school tests will fail if players bonus number is spun | Bug | 2018-11-06 | Andrew | 2018-11-08 | Fixed.
Baby stop tile gives a null pointer in the UIDraw function | Bug | 2018-11-06 | Conor | 2018-11-06 | Found the problem, shadowplayer being passed is null
Spin to win state doesnt inform as to which user is picking the number | Missing Feature | 2018-11-06 | Andrew, Conor | 2018-11-08 | Implemented as requested.
Retirement state IndexOutOfBoundsException | Bug | 2018-11-06 | Conor | 2018-11-12 | Fixed.
Retirement doesnt tell the player that they are in fact retiring | Missing Feature | 2018-11-06 | Conor | 2018-11-21 | Need a futher status indicator, separate to the eventMessage which informs the users as to what tile they are on.
Implment message strings for all decision request messages | Missing Feature | 2018-11-06 | Conor | 2018-11-08 | Replaced all outstanding strings
Tidy up UI | UI | 2018-11-07 | Conor | 2018-12-01 | Redid all UI screens in a neater manner.
Handle the case where a career change occurs before the player has a career card | Bug | 2018-11-07 | Andrew, Conor | 2018-11-08 | If the user has no card we now do nothing apart from add the card to their count
Ability to return sold cards to deck | Feature Request | 2018-11-08 | Conor | 2018-11-08 | Cards now readded to the rear of the deck using existing but unused methods
Unit tests for Bank/Player classes | Testing | 2018-11-08 | Andrew | 2018-11-16 | Unit tests created
Graduation choices event message incomplete | Bug | 2018-11-08 | Andrew | 2018-11-08 | String now complete
All messages need to have eventMessage implemented in the UI | UI | 2018-11-08 | Conor | 2018-11-08 | Implemented as requested.
eventMessage should be part of the LifeGameMessage class, not the subclasses | Architecture | 2018-11-08 | Conor | 2018-11-11 | Refactored code
Out of bounds exception in Night School | Bug | 2018-11-08 | Andrew | 2018-11-12 | Not currently occuring
Element not found in CollegeCareerCardDeck | Bug | 2018-11-09 | Andrew | 2018-11-12 | Being caused by running out of cards, solved by returning old cards to deck
FamilyStopTile not being set up/handled correctly at some stage | Bug | 2018-11-09 | Andrew
Entire window froze up when using the spinner GUI buttons | Bug | 2018-11-09 | Conor
Modify structure of messaging interface to remove premature abstraction | Architecture | 2018-11-10 | Conor | 2018-11-11 | Implemented as requested.
Potentially refactor tests to make use of Before/After | Testing | 2018-11-10 | Andrew, Conor | 2018-11-11 | Does not fit for integration tested, used for unit tests.
InitialisePlayerState does nothing | Redundant Code | 2018-11-10 | Andrew, Conor | 2018-11-11 | Deleted
Refactor gamestate | Coding Style | 2018-11-10 | Andrew, Conor | 2018-11-11 | Changed GameState from an interface to an abstract class
4 more college career cards | Missing Feature | 2018-11-15 | Andrew | 2018-11-16 | Need to make 4 more cards to meet the specs
Sit down and run through the specs | Other | 2018-11-15 | Andrew, Conor | 2018-12-01 | Done.
Need to send ShadowPlayer more than once per turn. | Feature Request | 2018-11-15 | Conor | 2018-12-01 | Refactored messaging interface to send shadowplayers in all requests.
clean up bulky tests | Coding Style | 2018-11-16 | Andrew, Conor
Redo sequence diagrams for startup sequence (modified by conor) | Documentation | 2018-11-25 | Conor | 2018-11-29 | Done.
Error: board has been configured incorrectly at the Family Stop Tile for player 2 | Bug | 2018-11-30 | Andrew
Add ShadowPlayer to EndTurnMessage | Missing Feature | 2018-12-12 | Conor | 2018-12-12 | Added.
Delete exit functions | Redundant Code | 2018-12-12 | Conor | n/a | Was actually already done.
CareerChange pompts a player with a CollegeCareer with StandardCareer options | Bug | 2018-12-13 | Andrew | 2018-12-14 | Fixed, career type was not being set correctly
ClassCastException when selling House | Bug | 2018-12-15 | Conor | 2018-12-16 | Spin procedure not being followed correctly
Refactoring of CardDecks to remove redundant abstract base class, generify deck | Refactor | 2018-12-15 | Andrew | 2018-12-15 | Completed, unit and integration tests all passing